## PROJECTS
ProjectID | ProjectName | Department | ProjectManager | Priority | Status | StartDate | PlannedEndDate | ActualEndDate | ProjectBudget | IsSOXRelevant
PRJ-001 | ERP System Upgrade | Finance | Anna Kowalski | High | Completed | 2024-01-10 | 2024-06-30 | 2024-07-45 | 850000 | Yes
PRJ-002 | SOX Remediation Program | Compliance | Marco Rossi | High | Active | 2024-02-01 | 2024-12-31 |  | 320000 | Yes
PRJ-003 | Cloud Infrastructure Migration | IT | David Chen | High | Active | 2024-03-15 | 2024-11-30 |  | 1200000 | Yes
PRJ-004 | HR System Implementation | HR | Sarah Johnson | Medium | Active | 2024-04-01 | 2024-10-31 |  | 450000 | No
PRJ-005 | Data Warehouse Consolidation | IT | Anna Kowalski | High | Active | 2024-01-20 | 2024-09-30 |  | 780000 | Yes
PRJ-006 | Internal Audit Tool Deployment | Compliance | Marco Rossi | High | Completed | 2024-01-05 | 2024-04-30 | 2024-05-12 | 230000 | Yes
PRJ-007 | Branch Network Expansion | Operations | Elena Petrova | Medium | Active | 2024-05-01 | 2024-12-31 |  | 560000 | No
PRJ-008 | Cybersecurity Framework Update | IT | David Chen | High | Active | 2024-02-15 | 2024-08-31 |  | 390000 | Yes
PRJ-009 | Finance Reporting Automation | Finance | Sarah Johnson | High | Delayed | 2024-03-01 | 2024-07-31 |  | 670000 | Yes
PRJ-010 | Vendor Management Platform | Procurement | James Okafor | Medium | Active | 2024-04-15 | 2024-11-30 |  | 310000 | No
PRJ-011 | Business Continuity Planning | Risk | Elena Petrova | High | Active | 2024-01-15 | 2024-06-30 |  | 180000 | Yes
PRJ-012 | Access Control Remediation | IT | David Chen | High | Completed | 2024-02-01 | 2024-05-31 | 2024-06-15 | 140000 | Yes
PRJ-013 | Regulatory Reporting Upgrade | Compliance | Marco Rossi | High | Active | 2024-05-01 | 2024-12-31 |  | 520000 | Yes
PRJ-014 | Budget Planning Tool Rollout | Finance | Anna Kowalski | Medium | On Hold | 2024-03-01 | 2024-09-30 |  | 290000 | Yes
PRJ-015 | Supply Chain Digitization | Operations | James Okafor | Medium | Active | 2024-04-01 | 2024-10-31 |  | 410000 | No
PRJ-016 | Identity Management Overhaul | IT | David Chen | High | Active | 2024-06-01 | 2025-01-31 |  | 680000 | Yes
PRJ-017 | SOX Training Program | Compliance | Elena Petrova | Medium | Completed | 2024-01-10 | 2024-03-31 | 2024-03-28 | 85000 | Yes
PRJ-018 | Financial Close Optimization | Finance | Anna Kowalski | High | Active | 2024-05-15 | 2024-11-30 |  | 430000 | Yes
PRJ-019 | Procurement Compliance Review | Procurement | James Okafor | Medium | Active | 2024-06-01 | 2024-12-31 |  | 195000 | Yes
PRJ-020 | IT Disaster Recovery Update | IT | David Chen | High | Delayed | 2024-02-01 | 2024-07-31 |  | 360000 | Yes
PRJ-021 | Internal Controls Documentation | Compliance | Marco Rossi | High | Active | 2024-03-01 | 2024-09-30 |  | 215000 | Yes
PRJ-022 | Payroll System Migration | HR | Sarah Johnson | Medium | Active | 2024-05-01 | 2024-11-30 |  | 375000 | Yes
PRJ-023 | Customer Data Governance | IT | Elena Petrova | High | Active | 2024-04-15 | 2024-10-31 |  | 490000 | No
PRJ-024 | Fixed Assets Management Update | Finance | Anna Kowalski | Medium | Completed | 2024-01-15 | 2024-05-31 | 2024-05-20 | 165000 | Yes
PRJ-025 | Change Management Framework | PMO | Marco Rossi | Medium | Active | 2024-06-01 | 2024-12-31 |  | 145000 | No
PRJ-026 | Audit Evidence Repository | Compliance | Elena Petrova | High | Active | 2024-03-15 | 2024-09-30 |  | 275000 | Yes
PRJ-027 | Tax Reporting Compliance | Finance | Sarah Johnson | High | Active | 2024-05-01 | 2024-12-31 |  | 340000 | Yes
PRJ-028 | Network Security Hardening | IT | David Chen | High | Completed | 2024-01-20 | 2024-04-30 | 2024-04-25 | 220000 | Yes
PRJ-029 | Operational Risk Framework | Risk | James Okafor | High | Active | 2024-04-01 | 2024-10-31 |  | 285000 | Yes
PRJ-030 | PMO Dashboard Implementation | PMO | Anna Kowalski | High | Active | 2024-06-01 | 2024-12-31 |  | 195000 | No

## CONTROLS
ControlID | ControlName | ControlDescription | ControlType | RiskRating | ControlOwner | Department | TestingFrequency | ITGCCategory | Status | LastTestedDate | EvidenceStatus
CTR-001 | Quarterly User Access Review | All user accounts in financial systems are reviewed quarterly to ensure access matches current job roles | Detective | High | David Chen | IT | Quarterly | Access Management | Active | 2024-06-30 | Collected
CTR-002 | Privileged Access Monitoring | Privileged and admin accounts are logged and reviewed monthly for unauthorized activity | Detective | Critical | David Chen | IT | Quarterly | Access Management | Active | 2024-06-30 | Collected
CTR-003 | Segregation of Duties Enforcement | No single user has both transaction initiation and approval rights in financial systems | Preventive | Critical | Anna Kowalski | Finance | Quarterly | Access Management | Active | 2024-06-30 | Pending
CTR-004 | New User Access Provisioning | New employees receive system access only after formal approval from their line manager and IT Security | Preventive | High | David Chen | IT | Quarterly | Access Management | Active | 2024-06-30 | Collected
CTR-005 | Terminated User Access Revocation | Access for all terminated employees is revoked within 24 hours of HR notification | Preventive | Critical | David Chen | IT | Quarterly | Access Management | Active | 2024-06-30 | Missing
CTR-006 | Change Management Approval | All changes to financial systems require formal approval through the change advisory board | Preventive | High | Marco Rossi | Compliance | Quarterly | Change Management | Active | 2024-03-31 | Collected
CTR-007 | Emergency Change Procedure | Emergency changes to production systems follow a documented expedited process with post-implementation review | Preventive | High | David Chen | IT | Semi-Annual | Change Management | Active | 2024-06-30 | Collected
CTR-008 | Change Testing and Validation | All system changes are tested in a non-production environment before deployment to production | Preventive | High | David Chen | IT | Quarterly | Change Management | Active | 2024-06-30 | Pending
CTR-009 | Release Management Control | Software releases follow a documented release management process with version control | Preventive | Medium | David Chen | IT | Semi-Annual | Change Management | Active | 2024-06-30 | Collected
CTR-010 | Patch Management Process | Security patches are applied within 30 days of release for critical systems | Preventive | High | David Chen | IT | Quarterly | Operations | Active | 2024-06-30 | Collected
CTR-011 | Backup and Recovery Testing | System backups are performed daily and recovery is tested quarterly | Detective | High | David Chen | IT | Quarterly | Operations | Active | 2024-06-30 | Collected
CTR-012 | System Availability Monitoring | Critical financial systems are monitored 24/7 with automated alerting for downtime | Detective | Medium | David Chen | IT | Quarterly | Operations | Active | 2024-06-30 | Collected
CTR-013 | Incident Management Process | All IT incidents affecting financial systems are logged tracked and resolved within defined SLAs | Detective | Medium | Marco Rossi | Compliance | Quarterly | Operations | Active | 2024-03-31 | Pending
CTR-014 | Data Backup Encryption | All backup data is encrypted using approved encryption standards | Preventive | High | David Chen | IT | Semi-Annual | Operations | Active | 2024-06-30 | Collected
CTR-015 | Journal Entry Approval | All manual journal entries above threshold require secondary approval before posting | Preventive | Critical | Anna Kowalski | Finance | Quarterly | Financial Reporting | Active | 2024-06-30 | Collected
CTR-016 | Financial Close Checklist | A formal checklist is completed and signed off by Finance Director for every monthly close | Preventive | High | Anna Kowalski | Finance | Quarterly | Financial Reporting | Active | 2024-06-30 | Collected
CTR-017 | Account Reconciliation Review | All balance sheet accounts are reconciled monthly and reviewed by Finance Manager | Detective | High | Anna Kowalski | Finance | Quarterly | Financial Reporting | Active | 2024-06-30 | Pending
CTR-018 | Variance Analysis Review | Budget versus actual variances exceeding 10% are formally investigated and documented | Detective | Medium | Anna Kowalski | Finance | Quarterly | Financial Reporting | Active | 2024-06-30 | Collected
CTR-019 | Financial Report Review | Monthly financial statements are reviewed and approved by CFO before distribution | Preventive | Critical | Sarah Johnson | Finance | Quarterly | Financial Reporting | Active | 2024-06-30 | Collected
CTR-020 | Intercompany Reconciliation | Intercompany transactions are reconciled monthly and differences resolved before close | Detective | High | Anna Kowalski | Finance | Quarterly | Financial Reporting | Active | 2024-03-31 | Missing
CTR-021 | SOD Conflict Monitoring | Automated monitoring detects and alerts on segregation of duties conflicts in financial systems | Detective | Critical | David Chen | IT | Quarterly | Access Management | Active | 2024-06-30 | Collected
CTR-022 | Password Policy Enforcement | Password complexity length and rotation requirements are enforced by system policy | Preventive | Medium | David Chen | IT | Semi-Annual | Access Management | Active | 2024-06-30 | Collected
CTR-023 | Multi-Factor Authentication | MFA is required for all remote access to financial systems | Preventive | High | David Chen | IT | Quarterly | Access Management | Active | 2024-06-30 | Collected
CTR-024 | Third Party Access Review | Access granted to vendors and contractors is reviewed quarterly and revoked when no longer needed | Detective | High | David Chen | IT | Quarterly | Access Management | Active | 2024-06-30 | Pending
CTR-025 | Data Retention Policy | Financial data is retained for minimum 7 years per regulatory requirements | Preventive | Medium | Marco Rossi | Compliance | Annual | Operations | Active | 2024-01-31 | Collected
CTR-026 | Procurement Approval Workflow | All purchases above defined thresholds require dual approval before order placement | Preventive | High | James Okafor | Procurement | Quarterly | Financial Reporting | Active | 2024-06-30 | Collected
CTR-027 | Invoice Matching Control | Three-way matching of purchase order invoice and goods receipt is performed before payment | Preventive | Critical | James Okafor | Procurement | Quarterly | Financial Reporting | Active | 2024-06-30 | Collected
CTR-028 | Payment Authorization Control | All payments above threshold require CFO approval before processing | Preventive | Critical | Sarah Johnson | Finance | Quarterly | Financial Reporting | Active | 2024-06-30 | Collected
CTR-029 | Fixed Asset Verification | Physical verification of fixed assets is performed annually and reconciled to the asset register | Detective | Medium | Anna Kowalski | Finance | Annual | Financial Reporting | Active | 2024-01-31 | Collected
CTR-030 | Expense Report Approval | All employee expense reports require manager approval before reimbursement | Preventive | Medium | Sarah Johnson | Finance | Quarterly | Financial Reporting | Active | 2024-06-30 | Collected
CTR-031 | IT Security Policy Review | IT Security policies are reviewed and updated annually and communicated to all staff | Preventive | Medium | Marco Rossi | Compliance | Annual | Operations | Active | 2024-01-31 | Collected
CTR-032 | Vulnerability Assessment | Quarterly vulnerability scans are performed on all financial system infrastructure | Detective | High | David Chen | IT | Quarterly | Operations | Active | 2024-06-30 | Collected
CTR-033 | Firewall Rule Review | Firewall rules are reviewed semi-annually and unauthorized rules are removed | Detective | High | David Chen | IT | Semi-Annual | Operations | Active | 2024-06-30 | Pending
CTR-034 | Data Loss Prevention Monitoring | DLP tools monitor and block unauthorized transfer of sensitive financial data | Preventive | High | David Chen | IT | Quarterly | Operations | Active | 2024-06-30 | Collected
CTR-035 | Logical Access Audit Log | All access to financial systems is logged and logs are retained for minimum 12 months | Detective | High | David Chen | IT | Quarterly | Access Management | Active | 2024-06-30 | Collected
CTR-036 | System Configuration Baseline | Financial system configurations are documented and deviations are detected and remediated | Preventive | High | David Chen | IT | Semi-Annual | Change Management | Active | 2024-06-30 | Collected
CTR-037 | Payroll Authorization Review | Payroll changes including new hires terminations and salary changes require HR Director approval | Preventive | Critical | Sarah Johnson | HR | Quarterly | Financial Reporting | Active | 2024-06-30 | Collected
CTR-038 | Tax Filing Review | All tax filings are reviewed by Tax Manager and approved by CFO before submission | Preventive | High | Sarah Johnson | Finance | Quarterly | Financial Reporting | Active | 2024-06-30 | Collected
CTR-039 | Regulatory Reporting Review | All regulatory reports are reviewed for accuracy before submission to regulators | Preventive | Critical | Marco Rossi | Compliance | Quarterly | Financial Reporting | Active | 2024-06-30 | Pending
CTR-040 | Audit Committee Reporting | Quarterly compliance status reports are presented to the Audit Committee | Detective | High | Marco Rossi | Compliance | Quarterly | Financial Reporting | Active | 2024-06-30 | Collected
CTR-041 | Business Continuity Plan Testing | BCP is tested annually with results documented and gaps remediated | Detective | Medium | Elena Petrova | Risk | Annual | Operations | Active | 2024-01-31 | Collected
CTR-042 | Risk Assessment Process | Formal risk assessments are conducted semi-annually for all critical business processes | Detective | High | Elena Petrova | Risk | Semi-Annual | Operations | Active | 2024-06-30 | Collected
CTR-043 | Whistleblower Hotline | An anonymous reporting mechanism exists and is communicated to all employees annually | Preventive | Medium | Marco Rossi | Compliance | Annual | Operations | Active | 2024-01-31 | Collected
CTR-044 | Code of Conduct Acknowledgment | All employees acknowledge the Code of Conduct annually | Preventive | Medium | Marco Rossi | Compliance | Annual | Operations | Active | 2024-01-31 | Collected
CTR-045 | SOX Training Completion | All control owners complete mandatory SOX training annually | Preventive | Medium | Elena Petrova | Compliance | Annual | Operations | Active | 2024-01-31 | Collected
CTR-046 | Internal Audit Independence | Internal audit function operates independently from management with direct reporting to Audit Committee | Preventive | High | Marco Rossi | Compliance | Annual | Financial Reporting | Active | 2024-01-31 | Collected
CTR-047 | Financial System Access Log Review | Automated review of financial system access logs for anomalous activity runs weekly | Detective | High | David Chen | IT | Quarterly | Access Management | Active | 2024-06-30 | Collected
CTR-048 | Outsourced Service Provider Review | Controls at outsourced service providers are reviewed via SOC reports annually | Detective | High | Marco Rossi | Compliance | Annual | Operations | Active | 2024-01-31 | Collected
CTR-049 | Anti-Fraud Monitoring | Automated transaction monitoring detects unusual patterns that may indicate fraud | Detective | Critical | Anna Kowalski | Finance | Quarterly | Financial Reporting | Active | 2024-06-30 | Collected
CTR-050 | Management Override Monitoring | Any management override of system controls is logged reviewed and approved by the Audit Committee | Detective | Critical | Marco Rossi | Compliance | Quarterly | Financial Reporting | Active | 2024-06-30 | Pending

## AUDIT FINDINGS
FindingID | ControlID | ProjectID | FindingTitle | Severity | RootCause | FindingOwner | DateIdentified | DaysOpen | RemediationDeadline | RemediationStatus | DateClosed | AuditCycle
FND-001 | CTR-005 | PRJ-012 | Terminated employee accounts not revoked within SLA | Critical | HR offboarding process does not notify IT Security automatically | David Chen | 2024-01-15 | 26 | 2024-02-15 | Closed | 2024-02-10 | 2024-Q1
FND-002 | CTR-003 | PRJ-001 | SOD conflict detected for 3 Finance users | Critical | Role assignment process does not check for SoD conflicts | Anna Kowalski | 2024-01-20 | 29 | 2024-02-20 | Closed | 2024-02-18 | 2024-Q1
FND-003 | CTR-017 | PRJ-005 | Account reconciliation completed 12 days after deadline | High | Understaffed finance team during peak period | Anna Kowalski | 2024-01-25 | 28 | 2024-02-25 | Closed | 2024-02-22 | 2024-Q1
FND-004 | CTR-008 | PRJ-003 | Change deployed to production without test evidence | High | Test environment was unavailable due to infrastructure issue | David Chen | 2024-02-05 | 25 | 2024-03-05 | Closed | 2024-03-01 | 2024-Q1
FND-005 | CTR-020 | PRJ-001 | Intercompany reconciliation not completed for January close | High | Manual process with no automated reminder or escalation | Anna Kowalski | 2024-02-10 | 27 | 2024-03-10 | Closed | 2024-03-08 | 2024-Q1
FND-006 | CTR-024 | PRJ-010 | 14 vendor accounts active beyond contract end date | High | No automated deprovisioning for vendor access | David Chen | 2024-02-15 | 26 | 2024-03-15 | Closed | 2024-03-12 | 2024-Q1
FND-007 | CTR-015 | PRJ-001 | 5 journal entries posted without secondary approval | Critical | System workflow bypassed due to month-end time pressure | Anna Kowalski | 2024-02-20 | 24 | 2024-03-20 | Closed | 2024-03-15 | 2024-Q1
FND-008 | CTR-010 | PRJ-008 | Critical security patches not applied within 30-day SLA | High | Patch management tool misconfigured for new server group | David Chen | 2024-03-01 | 27 | 2024-04-01 | Closed | 2024-03-28 | 2024-Q1
FND-009 | CTR-033 | PRJ-008 | Firewall review not completed for Q1 | High | Responsible engineer on extended leave with no backup assigned | David Chen | 2024-03-10 | 26 | 2024-04-10 | Closed | 2024-04-05 | 2024-Q1
FND-010 | CTR-039 | PRJ-013 | Regulatory report submitted without CFO review | Critical | Approval workflow not enforced in reporting tool | Marco Rossi | 2024-03-15 | 26 | 2024-04-15 | Closed | 2024-04-10 | 2024-Q1
FND-011 | CTR-001 | PRJ-016 | Q1 access review completed 18 days late | High | No automated reminder system for review deadlines | David Chen | 2024-04-05 | 25 | 2024-05-05 | Closed | 2024-04-30 | 2024-Q2
FND-012 | CTR-027 | PRJ-019 | 23 invoices paid without three-way match completion | Critical | Three-way match bypassed for urgent vendor payments | James Okafor | 2024-04-10 | 26 | 2024-05-10 | Closed | 2024-05-06 | 2024-Q2
FND-013 | CTR-016 | PRJ-018 | Financial close checklist missing CFO signature for March | High | Checklist submitted digitally but signature field was optional | Anna Kowalski | 2024-04-15 | 27 | 2024-05-15 | Closed | 2024-05-12 | 2024-Q2
FND-014 | CTR-021 | PRJ-016 | SoD monitoring tool offline for 11 days without detection | Critical | Monitoring tool failure not captured by system alerting | David Chen | 2024-04-20 | 749 | 2024-05-20 | In Progress |  | 2024-Q2
FND-015 | CTR-049 | PRJ-005 | Anti-fraud monitoring alerts not reviewed for 6 weeks | Critical | Alert review process not formally assigned to an owner | Anna Kowalski | 2024-04-25 | 744 | 2024-05-25 | In Progress |  | 2024-Q2
FND-016 | CTR-037 | PRJ-022 | Payroll changes processed without HR Director approval for 2 employees | Critical | Approval workflow had a configuration error after system update | Sarah Johnson | 2024-05-01 | 738 | 2024-06-01 | In Progress |  | 2024-Q2
FND-017 | CTR-013 | PRJ-003 | 8 IT incidents not resolved within SLA for April | Medium | Insufficient helpdesk capacity during cloud migration peak | Marco Rossi | 2024-05-05 | 734 | 2024-06-05 | In Progress |  | 2024-Q2
FND-018 | CTR-004 | PRJ-016 | 3 new users provisioned without documented manager approval | High | Approval form not required in expedited onboarding process | David Chen | 2024-05-10 | 729 | 2024-06-10 | In Progress |  | 2024-Q2
FND-019 | CTR-019 | PRJ-009 | April financial statements distributed before CFO review | Critical | Distribution list triggered automatically before approval step | Sarah Johnson | 2024-05-15 | 724 | 2024-06-15 | Open |  | 2024-Q2
FND-020 | CTR-050 | PRJ-002 | Management override of payment limit not reported to Audit Committee | Critical | Override reporting process not documented in procedure | Marco Rossi | 2024-05-20 | 719 | 2024-06-20 | Open |  | 2024-Q2
FND-021 | CTR-002 | PRJ-016 | Privileged account used for routine tasks over 30-day period | High | IT engineer used admin account for daily operations due to workload | David Chen | 2024-05-22 | 717 | 2024-06-22 | Open |  | 2024-Q2
FND-022 | CTR-028 | PRJ-018 | Payment of EUR 85000 processed without CFO approval | Critical | Payment system threshold setting was incorrect after upgrade | Sarah Johnson | 2024-05-25 | 714 | 2024-06-25 | Open |  | 2024-Q2
FND-023 | CTR-003 | PRJ-016 | New SoD conflict introduced during identity management project | High | Project team not consulted compliance team before role changes | Anna Kowalski | 2024-06-01 | 707 | 2024-07-01 | Open |  | 2024-Q2
FND-024 | CTR-011 | PRJ-020 | Backup recovery test failed for financial reporting database | Critical | Recovery procedure not updated after database migration | David Chen | 2024-06-05 | 703 | 2024-07-05 | Open |  | 2024-Q2
FND-025 | CTR-005 | PRJ-016 | 4 terminated contractors still have active system access | Critical | Contractor offboarding tracked separately from employee offboarding | David Chen | 2024-06-08 | 700 | 2024-07-08 | Open |  | 2024-Q2
FND-026 | CTR-017 | PRJ-018 | Q2 reconciliations for 5 accounts not yet started | High | Staff reallocation to financial close optimization project | Anna Kowalski | 2024-06-10 | 698 | 2024-07-10 | Open |  | 2024-Q2
FND-027 | CTR-015 | PRJ-009 | Journal entry approval threshold not updated after policy change | High | Policy change communication did not include system configuration update | Anna Kowalski | 2024-06-12 | 696 | 2024-07-12 | Open |  | 2024-Q2
FND-028 | CTR-039 | PRJ-013 | Q2 regulatory report review evidence not retained | High | Evidence storage process not followed by new team member | Marco Rossi | 2024-06-14 | 694 | 2024-07-14 | Open |  | 2024-Q2
FND-029 | CTR-023 | PRJ-016 | MFA bypass permitted for 2 service accounts without documentation | High | Exception process not formally documented or approved | David Chen | 2024-06-15 | 693 | 2024-07-15 | Open |  | 2024-Q2
FND-030 | CTR-008 | PRJ-003 | Emergency change deployed without post-implementation review | High | Time pressure during cloud migration led to skipped review step | David Chen | 2024-06-18 | 690 | 2024-07-18 | Open |  | 2024-Q2
FND-031 | CTR-020 | PRJ-018 | May intercompany reconciliation items unresolved at close | Medium | Counterparty entity did not provide supporting documentation | Anna Kowalski | 2024-06-19 | 689 | 2024-07-19 | Open |  | 2024-Q2
FND-032 | CTR-040 | PRJ-002 | Q1 Audit Committee report delivered 3 weeks late | Medium | Report preparation process not started early enough | Marco Rossi | 2024-06-20 | 688 | 2024-07-20 | Open |  | 2024-Q2
FND-033 | CTR-006 | PRJ-003 | Change advisory board quorum not met for 2 change approvals | Medium | Board members not available during cloud migration sprint | Marco Rossi | 2024-06-21 | 687 | 2024-07-21 | Open |  | 2024-Q2
FND-034 | CTR-018 | PRJ-009 | Variance investigation for Finance department not documented | Medium | Responsible analyst unclear on documentation requirements | Anna Kowalski | 2024-06-22 | 686 | 2024-07-22 | Open |  | 2024-Q2
FND-035 | CTR-032 | PRJ-008 | Q2 vulnerability scan completed 15 days late | Medium | Scanning tool license expired and renewal was delayed | David Chen | 2024-06-23 | 685 | 2024-07-23 | Open |  | 2024-Q2
FND-036 | CTR-024 | PRJ-010 | Quarterly vendor access review not documented for Q2 | High | New vendor manager unaware of review requirement | David Chen | 2024-06-24 | 684 | 2024-07-24 | Open |  | 2024-Q2
FND-037 | CTR-013 | PRJ-003 | Incident log shows 12 incidents with no resolution owner assigned | Medium | Incident management tool does not enforce owner assignment | Marco Rossi | 2024-06-25 | 683 | 2024-07-25 | Open |  | 2024-Q2
FND-038 | CTR-047 | PRJ-016 | Access log anomaly alerts not reviewed for 3 weeks | High | Alert review responsibility not included in team runbook | David Chen | 2024-06-26 | 682 | 2024-07-26 | Open |  | 2024-Q2
FND-039 | CTR-033 | PRJ-008 | Unauthorized firewall rule detected during Q2 review | Critical | Rule added during emergency maintenance without change ticket | David Chen | 2024-06-27 | 681 | 2024-07-27 | Open |  | 2024-Q2
FND-040 | CTR-050 | PRJ-021 | Management override log incomplete for Q2 period | High | Override logging process bypassed during system downtime | Marco Rossi | 2024-06-28 | 680 | 2024-07-28 | Open |  | 2024-Q2
Formulas:
DaysOpen = IF(AUDIT_FINDINGS[[#This Row],[RemediationStatus]]="Closed",AUDIT_FINDINGS[[#This Row],[DateClosed]]-AUDIT_FINDINGS[[#This Row],[DateIdentified]],TODAY()-AUDIT_FINDINGS[[#This Row],[DateIdentified]])

## MILESTONES
MilestoneID | ProjectID | MilestoneName | Phase | PlannedDate | ActualDate | Status | DelayDays | MilestoneOwner | IsCriticalPath
MST-001 | PRJ-001 | Project Charter Approved | Planning | 2024-01-20 | 2024-01-20 | Completed | 0 | Anna Kowalski | Yes
MST-002 | PRJ-001 | Requirements Gathering Complete | Planning | 2024-02-15 | 2024-02-18 | Completed | 3 | Anna Kowalski | Yes
MST-003 | PRJ-001 | Vendor Selection Finalized | Planning | 2024-03-01 | 2024-03-10 | Completed | 9 | Anna Kowalski | No
MST-004 | PRJ-001 | System Configuration Complete | Execution | 2024-05-01 | 2024-05-20 | Completed | 19 | Anna Kowalski | Yes
MST-005 | PRJ-001 | User Acceptance Testing Complete | Testing | 2024-06-15 | 2024-07-02 | Completed | 17 | Anna Kowalski | Yes
MST-006 | PRJ-002 | SOX Gap Assessment Complete | Planning | 2024-02-28 | 2024-03-05 | Completed | 5 | Marco Rossi | Yes
MST-007 | PRJ-002 | Remediation Roadmap Approved | Planning | 2024-03-31 | 2024-04-10 | Completed | 10 | Marco Rossi | Yes
MST-008 | PRJ-002 | Q1 Remediation Actions Complete | Execution | 2024-04-30 | 2024-05-15 | Completed | 15 | Marco Rossi | Yes
MST-009 | PRJ-002 | Q2 Remediation Actions Complete | Execution | 2024-07-31 |  | In Progress |  | Marco Rossi | Yes
MST-010 | PRJ-003 | Cloud Architecture Design Approved | Planning | 2024-04-01 | 2024-04-05 | Completed | 4 | David Chen | Yes
MST-011 | PRJ-003 | Development Environment Migrated | Execution | 2024-05-31 | 2024-06-10 | Completed | 10 | David Chen | Yes
MST-012 | PRJ-003 | Production Migration Phase 1 | Execution | 2024-07-31 |  | In Progress |  | David Chen | Yes
MST-013 | PRJ-003 | Production Migration Phase 2 | Execution | 2024-09-30 |  | Not Started |  | David Chen | Yes
MST-014 | PRJ-005 | Data Inventory Complete | Planning | 2024-02-29 | 2024-03-08 | Completed | 8 | Anna Kowalski | Yes
MST-015 | PRJ-005 | ETL Pipeline Development Complete | Execution | 2024-05-31 | 2024-06-20 | Completed | 20 | Anna Kowalski | Yes
MST-016 | PRJ-005 | Data Validation and Testing Complete | Testing | 2024-08-31 |  | In Progress |  | Anna Kowalski | Yes
MST-017 | PRJ-008 | Security Framework Assessment | Planning | 2024-03-15 | 2024-03-15 | Completed | 0 | David Chen | Yes
MST-018 | PRJ-008 | Critical Vulnerability Remediation | Execution | 2024-05-31 | 2024-06-05 | Completed | 5 | David Chen | Yes
MST-019 | PRJ-008 | Framework Documentation Complete | Execution | 2024-07-31 |  | In Progress |  | David Chen | No
MST-020 | PRJ-009 | Automation Requirements Defined | Planning | 2024-04-01 | 2024-04-15 | Completed | 14 | Sarah Johnson | Yes
MST-021 | PRJ-009 | Automation Tool Selected | Planning | 2024-04-30 | 2024-05-20 | Completed | 20 | Sarah Johnson | Yes
MST-022 | PRJ-009 | Phase 1 Automation Live | Execution | 2024-06-30 |  | Delayed |  | Sarah Johnson | Yes
MST-023 | PRJ-009 | Phase 2 Automation Live | Execution | 2024-07-31 |  | Not Started |  | Sarah Johnson | Yes
MST-024 | PRJ-016 | Identity Platform Selected | Planning | 2024-07-01 |  | In Progress |  | David Chen | Yes
MST-025 | PRJ-016 | Legacy System Decommission Plan | Planning | 2024-08-31 |  | Not Started |  | David Chen | No
MST-026 | PRJ-020 | DR Assessment Complete | Planning | 2024-03-31 | 2024-04-20 | Completed | 20 | David Chen | Yes
MST-027 | PRJ-020 | DR Plan Updated | Execution | 2024-05-31 |  | Delayed |  | David Chen | Yes
MST-028 | PRJ-020 | DR Test Scheduled | Execution | 2024-07-31 |  | Not Started |  | David Chen | Yes
MST-029 | PRJ-022 | Payroll Data Migration Plan | Planning | 2024-06-01 | 2024-06-05 | Completed | 4 | Sarah Johnson | Yes
MST-030 | PRJ-022 | Parallel Run Testing | Testing | 2024-09-30 |  | Not Started |  | Sarah Johnson | Yes

## BUDGET TRACKING
BudgetID | ProjectID | Project name | Month | PlannedSpend | ActualSpend | Variance | VariancePercent | Category | ApprovedBy
BGT-001 | PRJ-001 | ERP System Upgrade | 2024-01-01 | 85000 | 82000 | -3000 | -3.5294 | Labour | Anna Kowalski
BGT-002 | PRJ-001 | ERP System Upgrade | 2024-02-01 | 95000 | 98500 | 3500 | 3.6842 | Labour | Anna Kowalski
BGT-003 | PRJ-001 | ERP System Upgrade | 2024-03-01 | 120000 | 135000 | 15000 | 12.5 | Technology | Anna Kowalski
BGT-004 | PRJ-001 | ERP System Upgrade | 2024-04-01 | 180000 | 195000 | 15000 | 8.3333 | Technology | Anna Kowalski
BGT-005 | PRJ-001 | ERP System Upgrade | 2024-05-01 | 200000 | 218000 | 18000 | 9 | External | Anna Kowalski
BGT-006 | PRJ-001 | ERP System Upgrade | 2024-06-01 | 170000 | 168500 | -1500 | -0.88235 | Labour | Anna Kowalski
BGT-007 | PRJ-002 | SOX Remediation Program | 2024-02-01 | 25000 | 24500 | -500 | -2 | Labour | Marco Rossi
BGT-008 | PRJ-002 | SOX Remediation Program | 2024-03-01 | 28000 | 27000 | -1000 | -3.5714 | Labour | Marco Rossi
BGT-009 | PRJ-002 | SOX Remediation Program | 2024-04-01 | 32000 | 35500 | 3500 | 10.9375 | External | Marco Rossi
BGT-010 | PRJ-002 | SOX Remediation Program | 2024-05-01 | 35000 | 38000 | 3000 | 8.5714 | External | Marco Rossi
BGT-011 | PRJ-003 | Cloud Infrastructure Migration | 2024-03-01 | 80000 | 78000 | -2000 | -2.5 | Labour | David Chen
BGT-012 | PRJ-003 | Cloud Infrastructure Migration | 2024-04-01 | 120000 | 125000 | 5000 | 4.1667 | Technology | David Chen
BGT-013 | PRJ-003 | Cloud Infrastructure Migration | 2024-05-01 | 180000 | 210000 | 30000 | 16.6667 | Technology | David Chen
BGT-014 | PRJ-003 | Cloud Infrastructure Migration | 2024-06-01 | 220000 | 255000 | 35000 | 15.9091 | External | David Chen
BGT-015 | PRJ-005 | Data Warehouse Consolidation | 2024-01-01 | 60000 | 58000 | -2000 | -3.3333 | Labour | Anna Kowalski
BGT-016 | PRJ-005 | Data Warehouse Consolidation | 2024-02-01 | 75000 | 74000 | -1000 | -1.3333 | Labour | Anna Kowalski
BGT-017 | PRJ-005 | Data Warehouse Consolidation | 2024-03-01 | 90000 | 95000 | 5000 | 5.5556 | Technology | Anna Kowalski
BGT-018 | PRJ-005 | Data Warehouse Consolidation | 2024-04-01 | 110000 | 108000 | -2000 | -1.8182 | Technology | Anna Kowalski
BGT-019 | PRJ-008 | Cybersecurity Framework Update | 2024-02-01 | 35000 | 34000 | -1000 | -2.8571 | Labour | David Chen
BGT-020 | PRJ-008 | Cybersecurity Framework Update | 2024-03-01 | 45000 | 47000 | 2000 | 4.4444 | Technology | David Chen
BGT-021 | PRJ-008 | Cybersecurity Framework Update | 2024-04-01 | 60000 | 65000 | 5000 | 8.3333 | External | David Chen
BGT-022 | PRJ-009 | Finance Reporting Automation | 2024-03-01 | 55000 | 54000 | -1000 | -1.8182 | Labour | Sarah Johnson
BGT-023 | PRJ-009 | Finance Reporting Automation | 2024-04-01 | 80000 | 88000 | 8000 | 10 | Technology | Sarah Johnson
BGT-024 | PRJ-009 | Finance Reporting Automation | 2024-05-01 | 120000 | 142000 | 22000 | 18.3333 | External | Sarah Johnson
BGT-025 | PRJ-009 | Finance Reporting Automation | 2024-06-01 | 150000 | 178000 | 28000 | 18.6667 | External | Sarah Johnson
BGT-026 | PRJ-016 | Identity Management Overhaul | 2024-06-01 | 45000 | 43000 | -2000 | -4.4444 | Labour | David Chen
BGT-027 | PRJ-020 | IT Disaster Recovery Update | 2024-02-01 | 30000 | 29500 | -500 | -1.6667 | Labour | David Chen
BGT-028 | PRJ-020 | IT Disaster Recovery Update | 2024-03-01 | 40000 | 42000 | 2000 | 5 | Technology | David Chen
BGT-029 | PRJ-020 | IT Disaster Recovery Update | 2024-04-01 | 55000 | 62000 | 7000 | 12.7273 | External | David Chen
BGT-030 | PRJ-022 | Payroll System Migration | 2024-05-01 | 35000 | 34000 | -1000 | -2.8571 | Labour | Sarah Johnson